## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Jessi | Kyra | Ricardo | Audrey | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 6 |  | 3
|  | Design architecture | Project Manager | Jessi, Kyra | 6 |  | 3 |  | 1.5 | 1.5 |  |  | 3
| Requirements |  |  |  |  | 11 |  | 14 |  |  |  |  | 0
|  | Gather | Project Manager, QA Testers, Developer | Jessi, Kyra, Ricardo, Audrey | 5 |  | 6 |  | 1.5 | 1.5 | 1.5 | 1.5 | 6
|  | Analyze | Project Manager, QA Testers, Developer | Jessi, Kyra, Ricardo, Audrey | 4 |  | 4 |  | 1 | 1 | 1 | 1 | 4
|  | Specify | Project Manager, QA Testers, Developer | Jessi, Kyra, Ricardo, Audrey | 2 |  | 4 |  | 1 | 1 | 1 | 1 | 4
| Documentation |  |  |  |  | 26 |  | 36 |  |  |  |  | 0
|  | Project Charter | QA Testers/Requirements Engineer | Ricardo, Audrey | 3 |  | 4 |  | 0 |  | 2 | 2 | 4
|  | Release Plan | QA Testers/Requirements Engineer | Ricardo, Audrey | 2 |  | 4 |  |  |  | 2 | 2 | 4
|  | Requirements Document | QA Testers/Requirements Engineer | Ricardo, Audrey | 4 |  | 4 |  |  |  | 2 | 2 | 4
|  | Project Plan | QA Testers/Requirements Engineer | Ricardo, Audrey | 3 |  | 6 |  | 0 |  | 3 | 3 | 6
|  | Architecture Document | QA Testers/Requirements Engineer/Project Manager/Developer | Jessi, Kyra, Ricardo, Audrey | 4 |  | 4 |  | 1 | 1 | 1 | 1 | 4
|  | Test Report | QA Testers/Requirements Engineer | Audrey, Ricardo | 8 |  | 8 |  |  |  | 4 | 4 | 8
|  | User Guide & System Admin Doc | QA Testers/Requirements Engineer | Audrey, Ricardo | 2 |  | 6 |  |  |  | 2 | 4 | 6
Coding | [6 empty] | 0 | [5 empty] | 0
Iteration 1: | Development |  |  |  |  | 53 |  | 50 |  |  |  |  | 0
|  | Create Database Schema | Developer | Jessi | 5 |  | 5 |  | 5 |  |  |  | 5
|  | Research and learn new language and environment | Developer | Jessi, Kyra | 15 |  | 10 |  | 5 | 5 |  |  | 10
|  | Set up Firebase | Developer | Jessi | 7 |  | 12 |  | 12 |  |  |  | 12
|  | Create frontend design | Developer | Kyra | 15 |  | 10 |  |  | 10 |  |  | 10
|  | Create Methods for Log-in Page and Dashboard | Developer | Kyra, Jessi | 4 |  | 4 |  | 2 | 2 |  |  | 4
|  | Test Methods | Developer | Kyra, Jessi | 5 |  | 6 |  | 3 | 3 |  |  | 6
|  | Unit Testing | Developer, QA Testers/Requirements Engineer | Ricardo, Audrey, Jessi | 2 |  | 3 |  | 1 | 1 | 1 |  | 3
| Analysis |  |  |  |  | 8 |  | 6 |  |  |  |  | 0
|  | System Testing | Developer | Kyra, Jessi | 3 |  | 2 |  | 1 | 1 |  |  | 2
|  | Bug fix as required | Developer | Jessi, Kyra | 3 |  | 2 |  | 1 | 1 |  |  | 2
|  | Evaluate needs for next iteration | Project Manager | Jessi, Kyra, Ricardo, Audrey | 2 |  | 2 |  | 0.5 | 0.5 | 0.5 | 0.5 | 2
Iteration 2: | Design |  |  |  |  | 19 |  | 12 |  |  |  |  | 0
|  | Implement any design changes | Project Manager, Developer | Jessi, Kyra | 5 |  | 4 |  | 2 | 2 | 0 | 0 | 4
|  | Risk analysis | Project Manager | Jessi, Kyra | 3 |  | 2 |  | 1 | 1 |  |  | 2
|  | Create Carousel | Developer | Ricardo, Kyra | 1 |  | 1 |  |  | 0.5 | 0.5 |  | 1
|  | Implement Design Changes | Developer | Jessi, Kyra | 5 |  | 2 |  | 1 | 1 |  |  | 2
|  | Continue to create UX and UI design for front end | Developer | Kyra | 5 |  | 3 |  |  | 3 |  |  | 3
| Development |  |  |  |  | 19 |  | 15 |  |  |  |  | 0
|  | Review requirements | QA Testers/Requirements Engineer/Project Manager/Developer | Jessi, Kyra, Ricardo, Audrey | 1 |  | 1 |  | 0.25 | 0.25 | 0.25 | 0.25 | 1
|  | Commect database to front end | Developer | Jessi, Kyra | 10 |  | 8 |  | 4 | 4 |  |  | 8
|  | Implement UI | Developer | Kyra, Jessi | 6 |  | 4 |  | 2 | 2 |  |  | 4
|  | Continue Unit Testing | Requirements Engineer | Ricardo, Audrey | 2 |  | 2 |  |  | 1 | 1 |  | 2
| Analysis |  |  |  |  | 6 |  | 4 |  |  |  |  | 0
|  | System Testing | Developer | Kyra, Jessi | 2 |  | 1 |  | 0.5 | 0.5 |  |  | 1
|  | Bug fix as required | Developer | Jessi, Kyra | 2 |  | 2 |  | 1 | 1 |  |  | 2
|  | Evaluate needs for next iteration | Project Manager | Jessi, Kyra, Ricardo, Audrey | 2 |  | 1 |  | 0.25 | 0.25 | 0.25 | 0.25 | 1
Iteration 3: | Design |  |  |  |  | 2 |  | 3 |  |  |  |  | 0
|  | Implement any design changes to dashboard, donation pages and log-in pages | Project Manager, Developer | Jessi, Kyra | 2 |  | 3 |  | 1.5 | 1.5 |  |  | 3
| Development |  |  |  |  | 20 |  | 7 |  |  |  |  | 0
|  | Review requirements | Developer, QA Testers/Requirements Engineer | Jessi, Kyra, Ricardo, Audrey | 2 |  | 1 |  | 0.25 | 0.25 | 0.25 | 0.25 | 1
|  | Successful Donation Page | Developer | Kyra, Jessi | 10 |  | 4 |  | 2 | 2 |  |  | 4
|  | Successful Connection from donation to database | Developer | Jessi, Kyra | 8 |  | 2 |  | 1 | 2 |  |  | 3
| Analysis |  |  |  |  | 3 |  | 1 |  |  |  |  | 0
|  | Deploy Web Application | Developer | Jessi, Kyra | 3 |  | 1 |  | 0.5 | 0.5 |  |  | 1
Total |  |  |  |  | 173 | 173 | 152 | 151 | 53.75 | 52.25 | 23.25 | 22.75 | 152